## Tasks
ID | Task Name | Category | Priority | Status | Start Date | Due Date | Estimated Hours | Actual Hours | % Complete | Dependencies | Notes
1 | School Academic Rules | Task | High | In Progress | 2026-02-01 | 2026-02-28 | 6 | 0 | 10% | - | Handle the logic: AppSchoolRules have Rule Name{Attendance, Percentage, etc}. AppFilter have filters optin like >, <, == etc. AppPromotionRules have Rules required for promotions like Attandance > 75%. AppClasses have the classes of school. AppSections is sections of classes. AppSubjects have the subject releted to classes
2 | Tenat User Creation | Bug | High | Done | 2026-02-23 | 2026-02-28 | 3 | 1 |  |  | When Adding new user to tenant (using super master login) its showing unauthrized.
3 | Edit Tenant & user | Bug | High | Done | 2026-02-24 | 2026-02-28 | 1 | 1 |  |  | The Edit pop up for tenant not opening & for User while editing and saving giving error.

## Lists (hidden)
Status | Category | Priority
Not Started | Task | High
In Progress | Bug | Medium
On Hold | Feature | Low
Done | Improvement
Blocked | Testing